Summary of Phase 3 Process

- PCC Decision and Approval

  - Parochial Church Councils (PCCs) vote to participate in the Minster Community (MC) based on the final proposal.

  - The Joint Archdeacon Mission Committee (JAMC) recommends the formation of the MC to the Bishop and Trustee Board.

  - The Bishop and Trustee Board provide final approval.

- Transition of Support

  - Contracted facilitators conclude their work at this stage.

  - Ongoing support for the MC will be provided by the Parish Transition and Ministry Department and the Archdeacons’ Office.

- Appointment of Oversight Minister (OM)

  - The process to appoint an OM begins. This may be:

    - A short transitional role (approximately 6 months) while a permanent appointment is made, or

    - A longer interim role (up to 3 years) as the MC establishes itself.

- Formation of Interim Oversight Group

  - An Interim MC Oversight Group is created to work alongside the OM and support Phase 3 activities.

  - This group may consist of members from the Phase 2 Coordinating Group or new volunteers.

  - A Minster Community may wish to form other key groups or communities of practice – such as a Safeguarding Group, Focal Ministry Group.

  - The interim Oversight Group will be given the template Memorandum of Understanding at this stage for information.

- Launch Service

  - Phase 3 begins with a Launch Service where the Bishop commissions:

    - The OM

    - The Oversight Group

    - All members of the congregations as they start their journey together.

- Memorandum of Understanding (MOU) –

  - An MOU is developed to outline the intentions and mutual understanding of all parties in terms of how parishes work together as a Minster Community. It will take the actions of the proposal and outlines how parishes work together to implement it.

  - There will be a template provided by the Archdeacon’s office which the Interim Oversight Group and the Oversight Minister will edit to suit the MC.

  - This will then be sent to all PCCs to sign the commitment.

- Ministry Discernment

    - In the discernment and forming of the whole Minster Community ministry team – one that can gather and support one another

  - A gathering of all ministers across the MC to reflect on their roles.

    - Share about the mission and aims of the Minster Community and how ministry will be part of that to enable individual prayerful discernment

    - Conversation about how ministry will be rooted and shared.

  - Individual discernment conversations for incumbents and associate ministers regarding their current roles and potential MC-wide responsibilities.

    - Conversations will take place with the Oversight Minster/ Archdeacon/ Bishop/ local incumbent (The Oversight Minister will keep track of these conversations)

  - Identify named person(s) (this could be a focal minister or member of clergy), for each benefice / parish as appropriate. Discernment led by local PCCs in collaboration with the designated incumbent and Oversight Minister. Safer recruitment process will be followed.

  - Outcomes may include:

    - Licensing ministers beyond their existing roles

    - New working agreements

  - Memoranda of Agreement (MOA) will then be created between ministers to define terms of collaboration. This work will be supported by the Archdeacon’s office.

- Formation of Key Groups

  - Minster Community wide Resourcing Ministry Group:

    - Works closely with the OM. Gathering to resource one another for the ministry across the MC as they enable others in the MC.

    - Includes stipendiary ministers those holding MC wide roles.

    - This team will support the whole ministry team of the MC

    - Will hold the mission of the MC

  - Minster Community Oversight Group [Transitioning from the Interim Oversight Group]:

    - A representative governance group (e.g., JCC or similar structure).

    - Handles MC-wide governance including financial and safeguarding matters and MC wide administration as informed by the MC proposal.

    - If a JCC is not formed, a core group will be established to manage overarching responsibilities and clarify parish-level governance.

- Refocusing on Mission

  - With structures in place, the MC can incorporate and honour its proposal and missional priorities.

  - Engage with schools to implement missional initiatives in light of the Storyboards and discerned response.

  - Participate in a planned Vision Day to:

    - Reflect on next missional steps to continue implementing the proposal.

    - Celebrate the work already implemented in the first 6 months

- At the 12 month point

  - One year review of the initial implementation plan, the ministry team formation

  - The MOU can then be reviewed and amended as required to take the MC forward.